## Appendix B-Budget & Cash Flow
APPENDIX B-PROJECT BUDGET & CASH FLOW
PROJECT IDENTIFICATION AND PROPOSED FUNDING
HRTAC Project Title: | I-264 Interchange Improvements- 64 WB Ramp to I-264 EB (UPC 57048)
Scope of Project Services: | Project Services to support the CN Phase for I-264 Interchange Improvements- 64 WB Ramp to I-264 EB (Parent UPC 57048/Child UPC 108042)
Recipient Entity: | Virginia Department of Transportation
Project Contact Information: | Tony Gibson (757) 556-7885
Baseline Schedule: | CN: Advertisement April 2016 - CN End October 2019
PROJECT COSTS & FUNDING SOURCE
Project Cost Category | Total Project Costs | HRTAC PayGo Funds | HRTAC Financed Funds | Description Other Sources of Funds | Amount Other Sources of Funds | Recipient Entity Funds
Design Work |  |  | 0 | Fed/State |  | 0
Engineering
Environmental Work
Right-of-Way Acquisition
Construction | 137023653 | 137023653
Contract Administration
Testing Services
Inspection Services
Capital Asset Acquisitions
Other
Total Estimated Cost | 137023653 | 137023653 | 0 | 0 | 0 | 0
FISCAL YEAR ANNUAL PROJECT CASH FLOW
| Total Fiscal Year 2017 |  | Total Fiscal Year 2018 |  | Total Fiscal Year 2019 |  | Total Fiscal Year 2020
Project Phase | PayGo | Financed | PayGo | Financed | PayGo | Financed | PayGo | Financed
Design Work
Engineering
Environmental Work
Right-of-Way Acquisition
Construction | 22402977 |  | 64831612 |  | 41680228 |  | 8108836
Contract Administration
Testing Services
Inspection Services
Capital Asset Acquisitions
Other
Total Estimated Cost | 22402977 | 0 | 64831612 | 0 | 41680228 | 0 | 8108836 | 0
Please Note: If additional years are needed, please submit a separate form with additional columns
FISCAL YEAR ESTIMATED PROJECT CASH FLOW
| FY 17 Mthly Cash Flow |  | FY 18 Mthly Cash Flow |  | FY 19 Qtrly Cash Flow |  | FY 20 Qtrly Cash Flow
| PayGo | Financed | PayGo | Financed | PayGo | Financed | PayGo | Financed
July |  |  | 3522582 |  | 4007715 |  | 1837956
August |  |  | 3656171 |  | 4007715 |  | 1254176
September |  |  | 4457715 |  | 4007715 |  | 1254176
October |  |  | 5793619 |  | 4007715 |  | 1254176
November | 1234904 |  | 5793619 |  | 3606942 |  | 1254176
December | 1902852 |  | 6722344 |  | 3606942 |  | 1254176
January | 2854628 |  | 6846998 |  | 3606942
February | 3121810 |  | 6679524 |  | 3206171
March | 3121810 |  | 5877981 |  | 3206171
April | 3255400 |  | 5744390 |  | 2805400
May | 3388991 |  | 5540447 |  | 2805400
June | 3522582 |  | 4196222 |  | 2805400
Total per Fiscal Year | 22402977 | 0 | 64831612 | 0 | 41680228 | 0 | 8108836 | 0
Please Note: If additional years are needed, please submit a separate form with additional columns
This attachment is certified and made an official attachment to the Standard Project Agreement document by the parties of this agreement.
Virginia Department of Transportation |  |  |  |  | Hampton Roads Transportation Accountability Commission
Signature |  |  |  |  | Signature
Commissioner |  |  |  |  | HRTAC Executive Director
Title |  |  |  |  | Title
Date |  |  |  |  | Date
Charles A. Kilpatrick, P.E.
Print name of person signing |  |  |  |  | Print name of person signing
Revised 7.8.14